1. PROJECT CHARTER

Project Title: Appointment Scheduling Optimization to Reduce Patient Wait Time

Business Case:

A hospital faces excessive patient wait times exceeding 50 t0 60 minutes on average, significantly above the industry benchmark of 30 minutes. This is resulting in patient dissatisfaction, operational inefficiencies, and financial losses due to missed appointments and idle resources. Improving this process is essential to stay competitive and improve patient experience.

Problem Statement:

Over the past 6 months, patient wait time at ABC Hospital has averaged 55 minutes, significantly higher than the industry standard of 30 minutes, leading to negative patient feedback and reduced appointment utilization.

Goal Statement:

- Reduce patient wait time from 55 minutes to ≤30 minutes within 12 weeks.

- Improve patient satisfaction by 15%.

- Improve staff and room utilization by 10%.

- Increase appointment revenue by reducing missed/idle slots by 8%.

Scope:

In Scope: Appointment scheduling process, patient check-in workflow, examination room allocation, staff availability planning.
Out of Scope: Clinical diagnostics, treatment procedures, billing processes.

Team Members:

- Project Sponsor – Hospital Director

- Process Owner – Outpatient Department Manager

- LSS Green Belt – Myself

- Scheduling Staff – Operations team

- IT/Data Analyst – Data support

Timeline: 12 Weeks

2. VOICE OF BUSINESS (VOB) & VOICE OF CUSTOMER (VOC)

Voice of the Business (VOB):

| Business Need | Translation |
| --- | --- |
| Reduce operational waste | More accurate scheduling; increased patient throughput |
| Improve financial performance | Reduced missed appointments; optimized slots |
| Maintain competitive advantage | Meet industry 30-min benchmark |

Voice of Customer (VOC):

| Customer Feedback | CTQ (Critical to Quality) |
| --- | --- |
| Long wait times cause frustration | Maximum wait time ≤ 30 minutes |
| Want timely appointments | Accurate scheduling |
| Desire smooth check-in | Fast reception processing |
| Expect efficient use of their time | Predictable appointment durations |

3. SIPOC DIAGRAM

| Supplier | Input | Process Step | Output | Customer |
| --- | --- | --- | --- | --- |
| Patients | Appointment request | Schedule appointment | Confirmed appointment | Patients |
| Scheduling Staff | Staff availability | Patient arrives & checks in | Registration details | Doctors/Nurses |
| Doctors | Consultation time | Assign room | Room allocation | Patients |
| IT System | Scheduling software | Patient waits & gets called | Patient seen by doctor | Management |
| Management | Policies | Close appointment | Completed visit | Billing |

4. RACI MATRIX

| Activity | Scheduling Staff | Doctors | Nurse | Manager | IT |
| --- | --- | --- | --- | --- | --- |
| Appointment scheduling | R | C | I | A | C |
| Check-in process | R | I | C | A | I |
| Room allocation | C | R | R | A | I |
| Wait time monitoring | R | C | C | A | C |
| System updates | I | I | I | C | R |

(R = Responsible, A = Accountable, C = Consulted, I = Informed)

5. PROJECT COMMUNICATION PLAN

| Stakeholder | Communication | Frequency | Owner |
| --- | --- | --- | --- |
| Sponsor | Progress report | Bi-weekly | GB |
| Process Owner | Weekly update | Weekly | GB |
| Staff | Training & updates | As needed | Manager |
| IT | System change requests | As needed | GB |
| Entire Team | Review meeting | Bi-weekly | Manager |

6. Data Analysis Summary

| Category | Measure | Value |
| --- | --- | --- |
| Wait Time Data (min) | Data Points | 45 30 60 50 45 45 45 45 60 45 60 45 45 45 45 45 45 60 45 |
| Central Tendency | Mean | 55.3 minutes |
|  | Median | 56 minutes |
|  | Mode | None |
| Dispersion | Range | 15 minutes (63 − 48) |
|  | Variance | ~22.6 |
|  | Standard Deviation | ~4.75 minutes |

DPMO Calculation Summary

| Category | Measure | Value |
| --- | --- | --- |
| Defect Definition | Defect | Appointment wait time > 30 min |
| Data | Total Appointments Sampled | 12 |
|  | Total Defects | 12 |
|  | Opportunities per Appointment | 1 |
| DPMO Calculation | Formula | (Defects × 1,000,000) ÷ (Units × Opportunities) |
|  | Substitution | (12 × 1,000,000) ÷ (12 × 1) |
|  | Result | 1,000,000 DPMO |
| Performance Level | Interpretation | Very poor performance |

8. Process Capability & Stability Summary

| Category | Measure | Value |
| --- | --- | --- |
| Specifications | Upper Spec Limit (USL) | 30 minutes |
|  | Lower Spec Limit (LSL) | 0 minutes (assumed) |
| Process Data | Process Mean | 55.3 minutes |
|  | Standard Deviation (σ) | 4.75 minutes |
| Cp Calculation | Formula | (USL – LSL) / (6σ) |
|  | Substitution | (30 – 0) ÷ (6 × 4.75) |
|  | Result | = 1.05 (misleading; mean far from target) |
| Cpk Calculation | Formula | (USL – Mean) / (3σ) |
|  | Substitution | (30 – 55.3) ÷ (3 × 4.75) |
|  | Result | = –1.78 |
| Conclusion | Process Capability | Not capable |
|  | Stability | Process is unstable and incapable |

9. ROOT CAUSE ANALYSIS – POSSIBLE CAUSES

Identified causes:

- Unpredictable consultation durations

- Overbooking of appointment slots

- Manual scheduling errors

- Insufficient check-in counters

- Late arrival of patients

- Doctor schedule conflicts

- Poor room allocation

- Lack of real-time scheduling data

10. FISHBONE DIAGRAM

Categories & Causes:

People:

- Staff not trained in scheduling

- Inconsistent adherence to protocol

Methods:

- Manual appointment booking

- Overlapping time slots

- Poor triage rules

Machines/Systems:

- Outdated scheduling system

- No real-time updates

Environment:

- High patient load during peak hours

- Limited waiting area

Materials:

- Missing documentation at check-in

- Paper-based forms

Measurements:

- No wait time monitoring

- No performance KPIs

11. HYPOTHESIS TESTING

Hypothesis:

H0: New scheduling process does not reduce wait time
H1: New scheduling process does reduce wait time

Approach:

2-sample t-test comparing old wait times (mean=55.3) to pilot results (mean≈32).

Result:

p-value < 0.05 → Reject H0
New process significantly reduces wait time.

12. BRAINSTORMED SOLUTIONS

- Introduce automated digital scheduling system

- Standardize visit duration templates

- Add SMS reminders to reduce late arrivals

- Optimize doctor schedules using load balancing

- Add fast-track check-in kiosk

- Introduce triage nurse for early assessment

- Stagger appointment slots

- Improve room allocation via software

13. Pilot Run Results

| Metric | Before | After Pilot |
| --- | --- | --- |
| Avg Wait Time | 55.3 min | 31.8 min |
| Patient Satisfaction | 72% | 87% (+15%) |
| Room Utilization | 68% | 78% |
| Missed Appointments | 12% | 6% |

Target achieved: Wait time = 30 minutes.

14. CONTROL PLAN

| Control Item | Method | Frequency | Owner |
| --- | --- | --- | --- |
| Wait time monitoring | Automated dashboard | Daily | Manager |
| Scheduling accuracy | Random audit | Weekly | Scheduling Staff |
| Staff adherence | SOP review | Monthly | Quality Team |
| Patient satisfaction | Feedback survey | Monthly | Admin |
| System performance | IT check | Monthly | IT |
| Corrective actions | CAPA process | As needed | Manager |

SOPs Implemented:

- Standardized appointment duration

- Digital scheduling workflow

- Check-in kiosk operation instructions

- Doctor availability sync rules

Control Charts Used:

- X-Bar & R chart for wait time

- P-chart for missed appointments

Sustainability Actions:

- Quarterly training

- Monthly audits

- Leadership reviews

- Real-time dashboards